## Sheet1
No. | Task Sheet Description | Responsible | Status | Hours of Work Remaining Until Completion
|  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1 | Design use case diagram | All | Completed | Hours of Work Remaining Until Completion Day 1: 3
2 | Design entity relationship diagram | All |  | Hours of Work Remaining Until Completion Day 2: 3
3 | Design class diagram | All
4 | Design system prototype | Hoang | In Process | Hours of Work Remaining Until Completion Day 4: 5; Hours of Work Remaining Until Completion Day 5: 5
5